## Dashboard
OVH - ENGINE |  |  | Next JOB
Date Report | :
Unit Code | : | DA25063
Model Unit | : | AXOR 2528
Project Code | : | SWI AMC
HM Start | :
Start Date | : | 28/11/2024
Day | :
Est. Finish | :
PROGRESS JOB
Plan |  | Actual
Noted delay due to (if any) : |  |  | Need Support
- Kendala tool untuk melepas flywheel engine - Ada pekerjaan engine unit LT2517 dan pekerjaan differential unit WT2534 - Kendala borongan tidak bisa keluar BPN |  |  | NO | PART NUMBER | DESC | QTY | POSITION

## Job List
MACHINE |  |  |  |  | ENGINE |  |  |  | LOCATION |  |  |  | NO :
MODEL |  | SERIAL NO | MACHINE CODE | HM | MODEL |  |  | SERIAL NO | WORKSHOP AMC
AXOR 2528 |  | MFJ400243NJ001273 | DA25063 |  | OM906 LA |  |  | 400953DO120941
NO | JOB PROGRES | [5 empty] | DAY |  |  | %
| Remark, |  |  |  | ACTION | QTY MP | HOURS | MAN HOURS | PLAN ACHIEV | ACTUAL ACHIEV
NOT READY FOR USE
No | Job Description |  |  |  | S/P
1 | Dissassembly, Investigation and part listing |  |  |  |  | 2 | 24 | 48 | 33.33% |  | 3 | 11.11%
2 | Assembly crankcase |  |  |  |  | 3 | 14 | 42 | 19.44% |  | 1.75 | 14%
3 | Install Cylinder Head |  |  |  |  | 3 | 8 | 24 | 11.11% |  | 1
4 | Completed engine |  |  |  |  | 3 | 8 | 24 | 11.11% |  | 1
5 | Install Transmission to Unit |  |  |  |  | 3 | 4 | 12 | 5.556% |  | 0.5
6 | Install Engine to Unit |  |  |  |  | 3 | 6 | 18 | 8.333% |  | 0.75
7 | Ground test Unit |  |  |  |  | 3 | 8 | 24 | 11.11% |  | 1
TOTAL | [6 empty] | 72 | 192 | 100% | 0%
Legend :
[5 empty] | S | Seri
[5 empty] | P | Paralel

## Part List
PN | DESC | QTY | Location | ETA Site | Status | Row Labels | Count of Status
A9060540605 | PUSH ROD | 2 | AMC | - | Ready | Ready | 100%
A4000161521 | SEAL, CYLINDER HEAD COVER / GASKET | 1 | AMC | - | Ready | Grand Total | 100%
A4001880180 | GASKET | 1 | AMC | - | Ready
A4002010080 | GASKET | 1 | AMC | - | Ready
A0239976848 | SEAL RETURN PLD | 6 | AMC | - | Ready
A9060540605 | PUSH ROD | 10 | AMC | - | Ready
A9060541401 | CAM FOLLOWER / NORMAL (TAPPET ROLLER) | 12 | BPN | - | Ready
A9060161420 | CYLINDER HEAD GASKET | 1 | BPN | - | Ready
A0209971148 | O-RINGS | 1 | BPN | - | Ready
A4000160380 | GASKET (SOLENOID ENGINE BRAKE) | 1 | BPN | - | Ready
A9062320080 | GASKET | 1 | BPN | - | Ready
A0020941580 | GASKET | 1 | BPN | - | Ready
A0289978045 | O-RINGS | 6 | BPN | - | Ready
A4000980280 | GASKET | 6 | BO | - | Ready
A4001420480 | GASKET | 3 | BO | - | Ready
A4002030280 | GASKET | 1 | BJM | - | Ready
A9060530358 | VALVE STEM SEAL | 18 | AMC | - | Ready
A4000910280 | GASKET (FUEL FEED PUMP) | 1 | AMC | - | Ready
A9061840280 | GASKET | 1 | AMC | - | Ready
A0289975648 | O RING PLD | 6 | AMC | - | Ready
A9060170860 | O -RING INJECTOR | 6 | AMC | - | Ready
A4001870280 | GASKET OIL TURBO | 1 | AMC | - | Ready
A9049900412 | LU COMBI-SCREW WITH BIHEXAGON SOCKET | 12 | AMC | - | Ready

## JSS Chart
No | Job Description | Weight% |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58
 | time axis 2024-08-28 to 2024-10-24
1 | Dissassembly, Investigation and part listing | PLAN | 33.3% | 2024-08-28: 11.1%; 2024-08-29: 11.1%; 2024-08-30: 11.1%
|  | ACTUAL | 33% | 2024-08-30: 2%; 2024-08-31: 5%; 2024-09-18: 8%; 2024-09-19: 8%; 2024-09-24: 10%
2 | Waiting Parts | PLAN | 1% | bar: 2024-09-25 to 2024-10-17
|  | ACTUAL | 1% | bar: 2024-09-25 to 2024-10-17
3 | Assembly crankcase | PLAN | 19% | 2024-10-18: 9.5%; 2024-10-19: 9.5%
|  | ACTUAL | 19% | 2024-10-18: 19%
4 | Install Cylinder Head | PLAN | 11% | 2024-10-20: 11%
|  | ACTUAL | 11% | bar: 2024-10-19 to 2024-10-20
5 | Completed engine | PLAN | 11% | 2024-10-21: 11%
|  | ACTUAL | 11% | 2024-10-20: 11%
6 | Install Transmission to Unit | PLAN | 6% | bar: 2024-10-22
|  | ACTUAL | 6% | bar: 2024-10-23
7 | Install Engine to Unit | PLAN | 8% | bar: 2024-10-23
|  | ACTUAL | 8% | bar: 2024-10-22
8 | Ground test Unit | PLAN | 11% | 2024-10-24: 11%
|  | ACTUAL | 11% | 2024-10-23: 11%
| Daily Plan (%) |  | 100.3% | 11.1% | 11.1% | 11.1% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 1% | 9.5% | 9.5% | 11% | 11% | 6% | 8% | 11%
| Cumulative Plan (%) |  |  | 11.1% | 22.2% | 33.3% | 33.3% | 33.3% | 33.3% | 33.3% | 33.3% | 33.3% | 33.3% | 33.3% | 33.3% | 33.3% | 33.3% | 33.3% | 33.3% | 33.3% | 33.3% | 33.3% | 33.3% | 33.3% | 33.3% | 33.3% | 33.3% | 33.3% | 33.3% | 33.3% | 33.3% | 33.3% | 33.3% | 33.3% | 33.3% | 33.3% | 33.3% | 33.3% | 33.3% | 33.3% | 33.3% | 33.3% | 33.3% | 33.3% | 33.3% | 33.3% | 33.3% | 33.3% | 33.3% | 33.3% | 33.3% | 33.3% | 33.3% | 34.3% | 42.8% | 52.3% | 63.3% | 74.3% | 80.3% | 88.3% | 99.3%
| Actual (%) |  | 89% | 0% | 0% | 2% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 8% | 8% | 0% | 0% | 0% | 0% | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 1% | 19% | 6% | 16% | 0% | 8% | 17% | 0%
| Cumulative Actual (%) |  |  | 0% | 0% | 2% | 7% | 7% | 7% | 7% | 7% | 7% | 7% | 7% | 7% | 7% | 7% | 7% | 7% | 7% | 7% | 7% | 7% | 7% | 15% | 23% | 23% | 23% | 23% | 23% | 33% | 33% | 33% | 33% | 33% | 33% | 33% | 33% | 33% | 33% | 33% | 33% | 33% | 33% | 33% | 33% | 33% | 33% | 33% | 33% | 33% | 33% | 33% | 34% | 52% | 58% | 74% | 74% | 82% | 99% | 99%

## Work Activity
WORK ACTIVITY
OVH
Machine Model |  |  |  | Serial Number |  |  |  | Machine Code |  | Date Planned | Service Meter |  |  | Branch/Site |  |  | Customer Name |  |  | Location of Machine
[10 empty] | DD / MM / YYYY | Hours Meter
AXOR 2528 |  |  |  | MFJ400243NJ001273 |  |  |  | DA25063 |  | 2024-09-26 |  |  |  | AMC |  |  | PT. PUTRA PERKASA ABADI |  |  | Workshop AMC
SPV | [5 empty] | Team Leader/QA/TO |  |  |  | Instruction | Dokumen workplan berfungsi sebagai rencana dan monitor proses pekerjaan dari shift ke shift. Berikan informasi yang jelas pada kolom yang telah disediakan dan catatan apabila diperlukan pada kolom note.
Signature | [5 empty] | Signature |  | :
Name |  | : | M PURWA PRASETYA |  |  | Name |  | : | HANAN FJ
ID No. |  | : | 23000487 |  |  | ID No. |  | : | 23001473 | Information | D : | Day | N : |  | Night |  | F : | Finish | NF : | Not Finish
Date |  | : |  |  |  | Date |  | :
No | Date |  |  |  | Shift (D/N) |  | Activities |  |  |  | PIC |  |  |  | Status (F/NF) | Note
1 | 28 Agustus 2024 |  |  |  | D |  | Remove Bottom guard |  |  |  | ARI |  |  |  | F
[7 empty] | remove oil pan |  |  |  | EKO |  |  |  | F
[7 empty] | open cylinder head | [7 empty] | F
[7 empty] | check damage tappet dan push rod | [7 empty] | F
[7 empty] | remove propeller shaft untuk evakuasi | [7 empty] | F
F
2 | 29 Agustus 2024 |  |  |  | D |  | Evakuasi Unit |  |  |  | ARI |  |  |  | F
[7 empty] | Lepas oil pan |  |  |  | EKO |  |  |  | F
[7 empty] | melepas propeller shaft | [7 empty] | F
[7 empty] | melepas air cleaner | [7 empty] | F
[7 empty] | melepas hose PTO | [7 empty] | F
[7 empty] | drain oli hidraulik | [7 empty] | F
[7 empty] | melepas clutch booster dan lever shift | [7 empty] | F
3 | 30 Agustus 2024 |  |  |  | D |  | melepas transmisi |  |  |  | ARI |  |  |  | F
[7 empty] | Melepas Clutch, Hose radiator, terminal motor starter, metering device |  |  |  | EKO |  |  |  | F
[7 empty] | melepas hose intercooler | [7 empty] | F
[7 empty] | melepas fan radiator | [7 empty] | F
[7 empty] | melepas wiring yang melindungi aktivitas pelepasan engine | [7 empty] | F
4 | 31 Agustus 2024 |  |  |  | D |  | Remove engine |  |  |  | ARI |  |  |  | F
[7 empty] | Membuat stand engine | [7 empty] | F
[7 empty] | move engine | [7 empty] | F
5 | 1 September - 17 September |  |  |  | D |  | pekerjaan engine unit LT2517 dan differential unit WT2534
6 | 18 Agustus 2024 |  |  |  | D |  | Remove Bottom guard |  |  |  | ARI |  |  |  | F
[7 empty] | remove oil pan |  |  |  | EKO |  |  |  | F
[7 empty] | Open cylinder head | [7 empty] | F
[7 empty] | remove propeller shaft untuk evakuasi unit | [7 empty] | F
[11 empty] | DIDIK |  |  |  | F
7 | 19 Agustus 2024 |  |  |  | D |  | Make stand engine |  |  |  | ARI |  |  |  | NF
[7 empty] | Remove flywheel |  |  |  | KHALIM |  |  |  | F
[7 empty] | Remove Timing case | [7 empty] | F
[7 empty] | Remove oil pan | [7 empty] | F
[7 empty] | remove camshaft | [7 empty] | F
[7 empty] | Remove tappet roller | [7 empty] | F
[7 empty] | cleaning short block | [7 empty] | F
8 | 24 Agustus 2024 |  |  |  | D |  | Make stand engine engine
check and cleaning camshaft
check and cleaning komponen cylinder head
9 | 25 Agustus - 17 Oktober 2024 |  |  |  | D |  | Waiting parts
10 | 2024-10-18 |  |  |  | D |  | Install tappet |  |  |  | DIDIK |  |  |  | F
[7 empty] | install camshaft |  |  |  | KHALIM |  |  |  | F
[7 empty] | install housing flywheel |  |  |  | ANDIKA |  |  |  | F
[7 empty] | retorque bolt housing flywheel | [7 empty] | F
[7 empty] | replace seal crankshaft | [7 empty] | F
[7 empty] | install dan retorque flywheel | [7 empty] | F
11 | 2024-10-19 |  |  |  | D |  | Install cylinder head |  |  |  | DIDIK |  |  |  | F
[7 empty] | torque cylinder 280 nm |  |  |  | KHALIM |  |  |  | F
[7 empty] | install pipe oil strainer |  |  |  | ANDIKA |  |  |  | F
[7 empty] | insall all PLD | [7 empty] | F
[7 empty] | install all injector | [7 empty] | F
[7 empty] | install vibration dumper | [7 empty] | F
[7 empty] | install waterpump, fuel pump, and oil cooler | [7 empty] | F
12 | 2024-10-20 |  |  |  | D |  | Install pushrod, rocker arm&adjust valve |  |  |  | KHALIM |  |  |  | F
[7 empty] | Install exhaust manifold |  |  |  | ANDIKA |  |  |  | F
[7 empty] | Install turbo charger |  |  |  | BAGAS |  |  |  | F
[7 empty] | Completed fuel line and filter | [7 empty] | F
[7 empty] | Install starting system | [7 empty] | F
[7 empty] | install compressor AC | [7 empty] | F
[7 empty] | install cover cyl head | [7 empty] | F
13 | 2024-10-22 |  |  |  | D |  | Install engine |  |  |  | DIDIK |  |  |  | F
[7 empty] | Completed engine |  |  |  | KHALIM |  |  |  | F
14 | 2024-10-23 |  |  |  | D |  | install Disc Clutch |  |  |  | DIDIK |  |  |  | F
[7 empty] | Install Transmission |  |  |  | KHALIM |  |  |  | F
[7 empty] | install muffler | [7 empty] | F
[7 empty] | install propeler | [7 empty] | F
[7 empty] | Fill Coolant, Oil | [7 empty] | F
[7 empty] | Test running | [7 empty] | F
[7 empty] | Ground test | [7 empty] | F
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44