## Dashboard
59.55%
0
OVH Engine PPA AMI |  |  | No | Job Description | Plan Day | Actual | Start date | Finish date | Remark
Date Report | : | 2025-11-10 | 1 | Preparation | 0.5 | 0.5 | 2025-10-25 | 2025-10-25
Unit Code | : | DA48111 | 2 | Washing Component | 0.5 | 0.5 | 2025-10-25 | 2025-10-25
Model Unit | : | Arocs4845 | 3 | Disassembly | 2 | 2 | 2025-10-26 | 2025-10-27
Project Code | : |  | 4 | Washing Part After Disasembly | 1 | 1 | 2025-10-28 | 2025-10-28
HM Start | : | 7676H / 204957KM | 5 | Measurement & Inspection | 2 | 2 | 2025-10-28 | 2025-10-28
Start Date | : | 2025-10-25 | 6 | Report (RPL) & Strip Down Report (SDR) | 2 | 2 | 2025-10-30 | 2025-10-31
Day | : | 16 | 7 | Order Parts | 20 | 11 | 2025-10-31 | 2025-11-20 | waiting part
Est. Finish | : | 2025-11-27 | 8 | Repair & Machining | 0 | 0
PROGRESS JOB |  |  | 9 | Assembly | 2 | 0
Plan |  | Actual | 10 | Testing & Performance Check | 0.5 | 0
100% |  | 59.55% | 11 | Final Inspection | 0.5 | 0
Noted delay due to (if any) :
1. Waiting penarikan part 2. Waiting SDR
|  |  | Target Day |  | 31 | 19
Recommended Parts List
|  |  | NO | COMPONENT GROUP | PART NUMBER | PART NAME |  | QTY | Eta | Remark | STO/DO/PO
|  |  | 1 | MOVING PART ENGINE | A4710100356 | LINER ONLY |  | 6 | 2025-11-17 | BASIC OVH | 6300012851
|  |  | 2 | MOVING PART ENGINE | A0239975545 | O-RING |  | 6 | 2025-11-17 | BASIC OVH | 6300012851
|  |  | 3 | MOVING PART ENGINE | A0229975345 | O-RING |  | 6 | 2025-11-17 | BASIC OVH | 6300012851
|  |  | 4 | MOVING PART ENGINE | A4710110259 | OIL SCRAPER RING |  | 6 | 2025-11-17 | BASIC OVH | 6300012851
|  |  | 5 | MOVING PART ENGINE | A4710303617 | PISTON |  | 6 | 2025-11-17 | PISTON SCRATCH | 6300012851
|  |  | 6 | MOVING PART ENGINE | A4710301240 | PARTS KIT, CRANKSH. BEAR. |  | 7 | 2025-11-17 | BASIC OVH | 6300012851
|  |  | 7 | MOVING PART ENGINE | A4710301060 | PARTS KIT, CONNECTING ROD |  | 6 | 2025-11-17 | BASIC OVH | 6300012851
|  |  | 8 | MOVING PART ENGINE | A4710300445 | TS FITTED BEARING |  | 1 | 2025-11-17 | BASIC OVH | 6300012851
|  |  | 9 | ENGINE HOUSING CYLINDER HEAD | A4700530158 | VALVE STEM SEAL |  | 24 | 2025-11-17 | BASIC OVH | 6300012851
|  |  | 10 | ENGINE HOUSING CYLINDER HEAD | A4710161820 | CYLINDER HEAD GASKET |  | 1 | 2025-11-17 | BASIC OVH | 6300012851
|  |  | 11 | ENGINE HOUSING CYLINDER HEAD | A4710160521 | SEAL, CYLINDER HEAD COVER |  | 1 |  | BASIC OVH
|  |  | 12 | ENGINE HOUSING CYLINDER HEAD | A4710160480 | CIRCUMFERENTIAL SEAL |  | 1 | 2025-11-17 | BASIC OVH | 6300012851
|  |  | 13 | OIL PAN | A4710140722 | OIL PAN SEAL |  | 1 | 2025-11-17 | BASIC OVH | 6300012851
|  |  | 14 | TIMING CASE | A4710150480 | SEAL |  | 1 | 2025-11-17 | BASIC OVH | 6300012851
|  |  | 15 | TIMING CASE | A0159974946 | RADIAL SHAFT SEALING RING |  | 1 | 2025-11-17 | BASIC OVH | 9000022297
|  |  | 16 | TIMING CASE | A4720180780 | ELASTOMER METAL SEAL |  | 1 | 2025-11-17 | BASIC OVH | 6300012851
|  |  | 17 | TIMING CASE | A0169975746 | CASSETTE-TYPE SEAL RING |  | 1 | 2025-11-13 | BASIC OVH
|  |  | 18 | TIMING CASE | A4720110280 | BEADED METAL SEAL |  | 1 | 2025-11-17 | BASIC OVH | 6300012851
|  |  | 19 | FUEL SYSTEM | A0179978945 | O-RING |  | 1 | 2025-11-17 | BASIC OVH | 6300012851
|  |  | 20 | FUEL SYSTEM | A0179978745 | O-RING |  | 6 | 2025-11-17 | BASIC OVH | 6300012851
|  |  | 21 | FUEL SYSTEM | A0179978845 | O-RING |  | 6 | 2025-11-17 | BASIC OVH | 6300012851
|  |  | 22 | FUEL SYSTEM | A0000171760 | SEALING RING |  | 6 | 2025-11-17 | BASIC OVH | 6300012851
|  |  | 23 | FUEL SYSTEM | A0179978645 | O-RING |  | 6 | 2025-11-17 | BASIC OVH | 6300012851
|  |  | 24 | AIR COMPRESSORE | A0239977145 | O-RING |  | 1 | 2025-11-20 | BASIC OVH | 10006253
|  |  | 25 | AIR COMPRESSORE | A4579970645 | SEALING RING |  | 2 | 2025-11-20 | BASIC OVH | 10006253
|  |  | 26 | AIR INTAKE | A4720980080 | SEAL |  | 6 | 2025-11-17 | BASIC OVH | 9000022297
|  |  | 27 | AIR INTAKE | A4720980880 | SEAL |  | 1 | 2025-11-17 | BASIC OVH | 9000022298
|  |  | 28 | EXHAUST SYSTEM | A5411870080 | GASKET Oil return line from exhaust gas turbocharger to crankcase |  | 1 | 2025-11-13 | BASIC OVH
|  |  | 29 | EXHAUST SYSTEM | A4711420680 | SEAL EXHAUST LINE AT TURBOCHARGER |  | 1 | 2025-11-17 | BASIC OVH | 9000022300
|  |  | 30 | EXHAUST SYSTEM | A4711420180 | METAL SEAL, MULTI-LAYER CYLINDERS NOS.1-3 |  | 1 | 2025-11-20 | BASIC OVH | 10006253
|  |  | 31 | EXHAUST SYSTEM | A4711420280 | METAL SEAL, MULTI-LAYER CYLINDERS NOS.4-6 |  | 1 | 2025-11-20 | BASIC OVH | 10006253
|  |  | 32 | EGR SYSTEM | A4712030680 | SEAL EXHAUST COOLER AT CYLINDER HEAD CYLINDERS 1-3 |  | 1 | 2025-11-20 | BASIC OVH | 10006253
|  |  | 33 | EGR SYSTEM | A4712030780 | SEAL EXHAUST COOLER AT CYLINDER HEAD CYLINDERS 4-6 |  | 1 | 2025-11-20 | BASIC OVH | 10006253
|  |  | 34 | ENGINE LUBRICATION | A4721841980 | SEAL OIL COOLER,OIL FILTER ON CYLINDER CRANKCASE |  | 1 | 2025-11-17 | BASIC OVH | 9000022300
|  |  | 35 | TURBOCHARGER | A0189973145 | O-RING |  | 1 | 2025-11-17 | BASIC OVH | 6300012851
|  |  | 36 | ENGINE COOLING | A4712031180 | SEAL |  | 1 | 2025-11-17 | BASIC OVH | 6300012851
|  |  | 37 | ENGINE | A4702000422 | VISCOUS CLUTCH |  | 1 | 2025-11-20 | INTERNAL SHORT | ROBBING
|  |  | 38 | ENGINE | A9605285982 | ACCORDIAN HOSE |  | 1 | 2025-11-20 | CRACK | ROBBING
|  |  | 39 | ENGINE | A4711427404 | EGR LINE |  | 1 | 2025-11-20 | CRACK | ROBBING

## JSS Form
MACHINE | [5 empty] | ENGINE |  |  | LOCATION |  | NO :
MODEL |  | SERIAL NO | MACHINE CODE |  | HM | MODEL |  |  | WS SSB
AROCS 4040 |  | W1T96421620532560 | AROCS 4040 |  |  | OM 471 LA
NO | JOB PROGRES | [5 empty] | DAY |  |  | %
| Remark, |  |  |  |  | ACTION | Plan Day | Actual
BREAKDOWN
No | Job Description
1 | Preparation |  |  |  |  | 9.1% | 0.5 | 0.5
2 | Washing Component |  |  |  |  | 9.1% | 0.5 | 0.5
3 | Disassembly |  |  |  |  | 9.1% | 2 | 2
4 | Washing Part After Disasembly |  |  |  |  | 9.1% | 1 | 1
5 | Measurement & Inspection |  |  |  |  | 9.1% | 2 | 2
6 | Report (RPL) & Strip Down Report (SDR) |  |  |  |  | 9.1% | 2 | 2
7 | Process Order Parts |  |  |  |  | 4.95% | 20 | 11 |  | 9%
8 | Repair & Machining |  |  |  |  | 0% | 0 |  |  | 0.45%
9 | Assembly |  |  |  |  | 0% | 2
10 | Testing & Performance Check |  |  |  |  | 0% | 0.5
11 | Final Inspection |  |  |  |  | 0% | 0.5
|  |  |  | TOTAL |  | 59.55% | 31 | 19

## List detail
Alur Proses Overhaul (OVH) Lengkap – Revisi
1. Preparation (Persiapan)
Menerima unit/komponen dari user.
Pemeriksaan kondisi awal & pencatatan HM / KM.
Pemasangan ID Tag & administrasi dokumen kerja.
Persiapan tools, equipment, dan area kerja.
2. Washing / Cleaning Awal
Pencucian unit/komponen secara menyeluruh (steam cleaner/degreaser).
Menghilangkan kotoran, lumpur, oli, dan grease.
Pengeringan dan penempatan di area kerja.
3. Disassembly (Pembongkaran)
Pembongkaran komponen sesuai prosedur OEM.
Pemisahan part reusable, repairable, dan scrap.
Dokumentasi kondisi part (foto / video).
4. Washing Part (Setelah Dibongkar)
Pencucian ulang part-part yang sudah dibongkar.
Membersihkan oil passage, kerak karbon, scale, sludge.
Gunakan washer khusus (solvent / ultrasonic cleaner bila ada).
Penataan part bersih di tray sesuai kelompok.
5. Measurement & Inspection (Pengukuran & Pemeriksaan)
Pengukuran part dengan special tools & measuring instruments.
Inspeksi visual (crack, wear, corrosion, scoring).
NDT (Non Destructive Test) bila diperlukan.
Pencatatan hasil measurement dalam inspection sheet.
6. Report Preliminary List (RPL) & Service Damage Report (SDR)
Pembuatan RPL: daftar part yang perlu diganti.
Pembuatan SDR: laporan kerusakan utama, penyebab, dan rekomendasi.
Review bersama Supervisor/Planner.
Approval dari user (jika ada mekanisme persetujuan).
7. Order Part List (Pengadaan Suku Cadang)
Penyusunan part list final.
Proses pemesanan part (warehouse/PO ke vendor).
Follow-up ketersediaan part & estimasi lead time.
8. Repair & Machining (jika diperlukan)
Perbaikan part yang masih bisa digunakan (repairable).
Proses machining (boring, honing, grinding, balancing, dsb).
Quality check hasil machining.
9. Assembly (Perakitan)
Persiapan assembly area (clean room).
Pemasangan part baru & hasil repair sesuai torque spec.
Menggunakan tools khusus (torque wrench, dial gauge).
Dokumentasi proses assembly.
10. Testing & Performance Check
Test performance di test bench / unit (engine dyno, transmission test stand).
Monitoring parameter sesuai spesifikasi OEM.
Adjustment & setting jika diperlukan.
Record hasil test.
11. Painting & Finishing
Pengecatan / coating jika diperlukan.
Labeling & tagging part.
Pemasangan nameplate atau sticker overhaul.
12. Quality Control & Final Inspection
QC check oleh inspector / QA.
Verifikasi dokumen overhaul (inspection sheet, test report, part list).
Approval release dari QA / Supervisor.
13. Delivery / Completed
Pembuatan dokumen serah terima (delivery report).
Penyerahan unit/komponen ke user.
Update histori unit dalam sistem maintenance (CMMS).
Close job order.

## JSS Chart
No | Job Description | Weight% |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50
 | time axis 2025-10-25 to 2025-12-13
1 | Preparation | Plan | 9% | bar: 2025-10-25
|  | Actual | 9% | bar: 2025-10-25
2 | Washing Component | Plan | 9% | bar: 2025-10-25
|  | Actual | 9% | bar: 2025-10-25
3 | Disassembly | Plan | 9% | bar: 2025-10-26
|  | Actual | 9% | bar: 2025-10-26 to 2025-10-27
4 | Washing Part After Disasembly | Plan | 9% | bar: 2025-10-28
|  | Actual | 9% | bar: 2025-10-28
5 | Measurement & Inspection | Plan | 9% | bar: 2025-10-29
|  | Actual | 9% | bar: 2025-10-29
6 | Report (RPL) & Strip Down Report (SDR) | Plan | 9% | bar: 2025-10-30
|  | Actual | 9% | bar: 2025-10-30
7 | Order Parts | Plan | 9% | bar: 2025-11-10; 2025-11-20
|  | Actual | 5% | bar: 2025-11-03
8 | Repair & Machining | Plan | 0%
|  | Actual | 0%
9 | Assembly | Plan | 0%
|  | Actual | 0%
10 | Testing & Performance Check | Plan | 0%
|  | Actual | 0%
11 | Final Inspection | Plan | 0%
|  | Actual | 0%
12 | #REF! | Plan | 0%
|  | Actual | 0%
13 |  | Plan | 0%
|  | Actual | 0%
14 |  | Plan | 0%
|  | Actual | 0%
15 |  | Plan | 0%
|  | Actual | 0%
16 |  | Plan | 0%
|  | Actual | 0%
17 |  | Plan | 0%
|  | Actual | 0%
18 |  | Plan | 0%
|  | Actual | 0%
19 |  | Plan | 0%
|  | Actual | 0%
| Daily Plan (%) | 63% |  | 18% | 9% | 0% | 9% | 9% | 9% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 6% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 3% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Cumulative Plan (%) |  |  | 18% | 27% | 27% | 36% | 45% | 54% | 54% | 54% | 54% | 54% | 54% | 54% | 54% | 54% | 54% | 54% | 60% | 60% | 60% | 60% | 60% | 60% | 60% | 60% | 60% | 60% | 63% | 63% | 63% | 63% | 63% | 63% | 63% | 63% | 63% | 63% | 63% | 63% | 63% | 63% | 63% | 63% | 63% | 63% | 63% | 63% | 63% | 63% | 63% | 63%
| Daily Actual (%) | #REF! |  | 18% | 5% | 4% | 9% | 9% | 9% | 0% | 0% | 0% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Cumulative Actual (%) |  |  | 18% | 23% | 27% | 36% | 45% | 54% | 54% | 54% | 54% | 59% | 59% | 59% | 59% | 59% | 59% | 59% | 59% | 59% | 59% | 59% | 59% | 59% | 59% | 59% | 59% | 59% | 59% | 59% | 59% | 59% | 59% | 59% | 59% | 59% | 59% | 59% | 59% | 59% | 59% | 59% | 59% | 59% | 59% | 59% | 59% | 59% | 59% | 59% | 59% | 59%

## Work Activity
WORK ACTIVITY
Repair Unit
Machine Model |  |  |  | Serial Number |  |  |  | Machine Code |  | Date Planned | Service Meter |  |  | Branch/Site |  |  | Customer Name |  |  | Location of Machine
[10 empty] | DD / MM / YYYY | Hours Meter
AROCS 4845k |  |  |  | W1T96423120648732 |  |  |  | 471922C0787916 |  | 2025-10-28 |  |  |  | AMI |  |  | PT. PUTRA PERKASA ABADI |  |  | WORKSHOP HAJU
SPV | [5 empty] | Team Leader/QA/TO |  |  |  | Instruction | Dokumen workplan berfungsi sebagai rencana dan monitor proses pekerjaan dari shift ke shift. Berikan informasi yang jelas pada kolom yang telah disediakan dan catatan apabila diperlukan pada kolom note.
Signature | [5 empty] | Signature |  | :
Name |  | : | M PURWA PRASETYA |  |  | Name |  | : | HANAN FJ
ID No. |  | : | 23000487 |  |  | ID No. |  | : | 23001473 | Information | D : | Day | N : |  | Night |  | F : | Finish | NF : | Not Finish
Date |  | : |  |  |  | Date |  | :
No | Date |  |  |  | Shift (D/N) |  | Activities |  |  |  | PIC |  |  |  | Status (F/NF) | Note
1 | 2025-10-24 |  |  |  | D |  | Check Blowby |  |  |  | M Khalim |  |  |  | F | Pengecekan pada jam 13.00 - 16.00
[7 empty] | PPM Unit |  |  |  | Didik |  |  |  |  | Temuan hose intake crack
[7 empty] | Check air sistem |  |  |  | Eko M |  |  |  |  | Temuan sensor humidity lepas
PPA
2 | 2025-10-24 |  |  |  | N |  | Remove Transmission |  |  |  | PPA |  |  |  | F | Kendala hujan jam 03.00 - 04.00
3 | 2025-10-25 |  |  |  | D |  | Remove Engine from Unit |  |  |  | M Khalim |  |  |  | NF | Kendala hujan jam 05.00 - 13.00
Eko M
4 | 2025-10-26 |  |  |  | D |  | Remove Engine from Unit |  |  |  | M Khalim |  |  |  | F | Kendala hujan jam 05.00 - 11.00
Eko M
Andika
PPA
5 | 2025-10-27 |  |  |  | D |  | Make Stand engine |  |  |  | Eko M |  |  |  | F
[7 empty] | Move engine to workshop |  |  |  | M Khalim
Andika
6 | 2025-10-28 |  |  |  | D |  | Remove fuel filter modul |  |  |  | M Khalim |  |  |  | NF | Continue
[7 empty] | Remove turbo |  |  |  | Eko M
[7 empty] | Remove Intake |  |  |  | Andika
Remove Exhaust
Remove Hardness engine
Remove modul oil cooler
Remove fuel system
Remove cylinder Head
Remove damper
Remove Flywel
7 | 2025-10-29 |  |  |  | D |  | Remove Piston cylinder no 1-6 |  |  |  | M Khalim |  |  |  | F | Continue RPL
[7 empty] | Cleaning Area Engine |  |  |  | Andika
[7 empty] | Make special tools tracker cylinder liner |  |  |  | Eko M
[7 empty] | Remove cylinder liner 3 & 5 |  |  |  | Syawal
Wraping part
Report
8 | 2025-10-30 |  |  |  | D |  | RPL |  |  |  | Didik |  |  |  | NF | Waiting ETA & Price
[7 empty] | SDR |  |  |  | Khalim
9 | 2025-10-31 |  |  |  | D |  | Quotation |  |  |  | Iqbal |  |  |  | F | Waiting Part Fulfill
Didik
10 | 2025-11-01 |  |  |  | D |  | Waiting Part |  |  |  | Iqbal |  |  |  | NF | Waiting Part Fulfill
11 | 2025-11-02 |  |  |  | D |  | Waiting Part |  |  |  | Iqbal |  |  |  | NF | Waiting Part Fulfill
12 | 2025-11-03 |  |  |  | D |  | Waiting Part |  |  |  | Iqbal |  |  |  | NF | Waiting Part Fulfill
13 | 2025-11-04 |  |  |  | D |  | Waiting Part |  |  |  | Iqbal |  |  |  | NF | Waiting Part Fulfill
14 | 2025-11-05 |  |  |  | D |  | Waiting Part |  |  |  | Iqbal |  |  |  | NF | Waiting Part Fulfill
15 | 2025-11-06 |  |  |  | D |  | Waiting Part |  |  |  | Iqbal |  |  |  | NF | Waiting Part Fulfill
16 | 2025-11-07 |  |  |  | D |  | Waiting Part
[11 empty] | Iqbal |  |  |  | NF | Waiting Part Fulfill
17 | 2025-11-08 |  |  |  | D |  | Waiting Part |  |  |  | Iqbal |  |  |  | NF | Waiting Part Fulfill
18 | 2025-11-09 |  |  |  | D |  | Waiting Part |  |  |  | Iqbal |  |  |  | NF | Waiting Part Fulfill
19 | 2025-11-10 |  |  |  | D |  | Waiting Part |  |  |  | Iqbal |  |  |  | NF | Waiting Part Fulfill
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44